## Final
ATTACHMENT E-1: Consultant SLBE/LBE Utilization Information Form
COMPANY NAME | [18 empty] | DATE
Civil Engineering, Environmental, and Right-of-Way Services for the Strobridge Avenue Extension Project
Estimated Staff Hours
TASK | Prime Company (Name) SLBE LBE Estimated Labor Hours | [7 empty] | (Prime) LABOR TOTAL HOURS | Sub-Consultants - Estimated Labor Hours | [8 empty] | SUB-CONSULANTS LABOR TOTAL HOURS | SLBE/LBE UTILIZATION PERCENTAGE
| (Name) Project Manager | (Name) Project Engr | (Name), Title | (Name), Title | (Name), Title | (Name), Title | (Name), Title | (Name), Title |  | (Name) Tier: 1 SLBE LBE | (Name) Tier: ___ ______ ______ | (Name) Tier: ___ ______ ______ | (Name) Tier: ___ ______ ______ | (Name) Tier: ___ ______ ______ | (Name) Tier: ___ ______ ______ | (Name) Tier: ___ ______ ______ | (Name) Tier: ___ ______ ______ | (Name) Tier: ___ ______ ______ |  | NON SLBE/LBE (%) | SLBE (%) | LBE (%)
STAGE 1
Task 1 - XXXXX
1.1 Xxxxxxxx
1.1.1 Xxxxxx
1.1.2 Xxxxxx
1.2 Xxxxxxxx
1.3 Xxxxxxxx
1.4 Xxxxxxxx
1.5 Xxxxxxxx
1.X Xxxxxxxx
1.X Xxxxxxxx
Subtotal Task 1
Task 2 - XXXXX
2.1 Xxxxxxx
2.1.1 Xxxxxxx
2.1.2 Xxxxxxx
2.2 Xxxxxxx
2.2.1 Xxxxxx
2.2.2 Xxxxxx
2.2.3 Xxxxxx
Subtotal Task 2
Total - STAGE 1
STAGE 2
Task 3 - XXXXX
3.1
3.2
3.3
Subtotal Task 3
Task 4 - XXXXX
4.1
4.2
4.3
4.4
Subtotal Task 4
Total - STAGE 2
STAGE 3
Task 5 - XXXXX
5.1
5.2
5.3
Subtotal Task 5
Total - STAGE 3
TOTAL FOR STAGES 1, 2 and 3
Sample

## Pre-Final
COMPANY NAME | [29 empty] | 2012-05-09
Proposal for Alameda County Public Works Agency
Civil Engineering, Environmental, and Right-of-Way Services for the Strobridge Avenue Extension Project
TASK | Mark Thomas & Company Labor Hours J. Sims L. Lau Project Civil Structural Project Sr Design Survey Project Survey Manager Leader Engr Engr Engr Manager Surveyor Crew | Company (Name) Labor Hours | [7 empty] | (Prime) LABOR TOTAL HOURS | Prime Percentage | Traffic TJKM (SLEB) |  | Environmental ICF |  | Hydrology Wreco (SLEB) |  | Hazardous Geocon |  | Geotech CE&G (SLEB) |  | VA Study VMS |  | Right of Way OPC |  | Landscape PGA (SLEB) |  | Mapping GeoCADD (SLEB) |  | SUBTOTAL Subs | TOTAL ESTIMATED COSTS
|  | (Name) Project Manager | (Name) Project Engr | (Name), Title | (Name), Title | (Name), Title | (Name), Title | (Name), Title | (Name), Title |  |  | Fee | Reimb | Fee | Reimb | Fee | Reimb | Fee | Reimb | Fee | Reimb | Fee | Reimb | Fee | Reimb | Fee | Reimb | Fee | Reimb
STAGE 1 | [11 empty] | 40550 | 3820 | 6138 |  | 7610 | 200 | 3300 | 200 | 44280 | 1668 | 13460 | 592 |  |  |  |  | 35919 | 5950 | 163687 | 207923
Task 1 - Project Management
1.1 Project Administration and Supervision
a. Supervise, Coordinate, and Monitor Team |  | 8 | 32 | [6 empty] | 40 | [20 empty] | 0
b. Attend Kickoff Meeting |  | 2 | 2 | [6 empty] | 4 | [20 empty] | 0
c. Data Collection/Document Reviews |  |  | 4 | [6 empty] | 4 | [20 empty] | 0
d. Monthly Invoices and Progress Reports |  | 2 | 16 | [6 empty] | 18 | [20 empty] | 0
e. Quality Assurance / Quality Control |  | 16 | [7 empty] | 16 | [20 empty] | 0
f. Maintain Project Schedule |  | 4 | 16 | [6 empty] | 20 | [20 empty] | 0
1.2 Project Meetings
a. PDT Meetings (4) |  | 8 | 8 | [6 empty] | 16 | [20 empty] | 0
b. Public Workshop Meetings (2) |  | 8 | 24 |  |  | 40 |  |  |  | 72 | [20 empty] | 0
c. Design Coordination Meetings (6) |  | 2 | 18 | [6 empty] | 20 | [20 empty] | 0
d. Client Meetings (5) |  | 10 | 10 | [6 empty] | 20 | [20 empty] | 0
e. Agency Meetings (2) |  | 4 | 4 | [6 empty] | 8 | [20 empty] | 0
Subtotal Task 1 |  | 52 | 80 |  |  | 40 | 0 | 0 | 0 | 172 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
Task 2 - Prepare Technical Information
2.1 Traffic Forecasting
2.1.1 Project Corridor Evaluation |  | 2 | 2 | [6 empty] | 4 |  | 27650 | 3820 | [16 empty] | 31470 | 31470
2.1.2 Traffic Operations Analysis |  | 1 | 2 | [6 empty] | 3 |  | 8880 | [17 empty] | 8880 | 8880
2.2 Base Mapping Development
2.2.1 Prepare Aerial Mapping |  | 1 | 7 |  |  |  | 14 | 58 | 68 | 148 | [17 empty] | 35919 | 5950 | 41869 | 41869
2.2.2 Supplemental Topographic Survey |  | 1 | 3 |  |  |  | 4 | 24 | 40 | 72 | [20 empty] | 0
2.2.3 Research and Data Collection |  |  | 3 |  |  | 16 | 4 | 16 |  | 39 | [20 empty] | 0
2.2.4 Utility Investigation |  |  | 3 |  |  | 16 |  |  |  | 19 | [20 empty] | 0
2.2.5 Record Boundary | [6 empty] | 24 | 48 |  | 72 | [20 empty] | 0
2.3 Environmental Impact Analysis |  | 2 | 2 | [6 empty] | 4 | [5 empty] | 4770 | 200 | 3300 | 200 | [10 empty] | 8470 | 8470
2.4 Geotechnical Investigations |  | 2 | 4 | [6 empty] | 6 | [9 empty] | 44280 | 1668 | [8 empty] | 45948 | 45948
Subtotal Task 2 |  | 9 | 26 |  |  | 32 | 46 | 146 | 108 | 367 |  | 36530 | 3820 |  |  | 4770 | 200 | 3300 | 200 | 44280 | 1668 | [6 empty] | 35919 | 5950 | 136637 | 136637
Task 3 - Develop Alternatives
3.1 Develop Conceptual Alternatives |  | 16 | 120 | 40 |  | 216 |  |  |  | 392 |  | 4020 |  | 6138 |  | 2840 | [13 empty] | 12998 | 12998
Subtotal Task 3 |  | 16 | 120 | 40 |  | 216 |  |  |  | 392 |  | 4020 |  | 6138 |  | 2840 | [13 empty] | 12998 | 12998
Task 4 - Prepare Alternative Analysis
4.1 Develop Evaluation Criteria, Project Reference Sheets & Tech Memo |  | 8 | 68 | [6 empty] | 76 | [20 empty] | 15256
4.2 Identify and Screen Alternatives |  | 4 | 80 | 16 | [5 empty] | 100 | [20 empty] | 19100
4.3 Two Day Improvements Prioritization Workshops |  | 4 | 16 | [6 empty] | 20 | [11 empty] | 13460 | 592 | [6 empty] | 14052 | 18224
4.4 Determine Viability of Alternatives |  | 4 | 24 | [6 empty] | 28 | [20 empty] | 5708
Subtotal Task 4 |  | 20 | 188 | 16 | [5 empty] | 224 | [11 empty] | 13460 | 592 | [6 empty] | 14052 | 58288
STAGE 2 | [11 empty] | 4760 |  | 32897 | 5445 | 15610 | 400 |  |  |  |  | 26328 | 2149 | 15180 | 500 | 9780 | 291 |  |  | 113340 | 204038
Task 5 -
5.1 | [13 empty] | 2000 | [15 empty] | 2000 | 2000
5.2 |  | 4 | 8 | [6 empty] | 12 |  |  |  | 20698 |  | 6510 | 100 | [12 empty] | 27308 | 29944
5.3 |  | 4 | 8 | [6 empty] | 12 |  |  |  | 10199 | 5445 | 3635 | 100 | [12 empty] | 19379 | 22015
Subtotal Task 5 |  | 8 | 16 | [6 empty] | 24 |  |  |  | 32897 | 5445 | 10145 | 200 | [12 empty] | 48687 | 53959
Task 6 -
6.1 |  | 8 | 24 | [6 empty] | 32 |  | 4760 | [17 empty] | 4760 | 11568
6.2 |  | 8 | 8 | 8 | [5 empty] | 24 | [5 empty] | 2285 | 100 |  |  |  |  | 26328 | 2149 | [6 empty] | 30862 | 35918
6.3 |  | 2 | 16 | 4 | [5 empty] | 22 | [20 empty] | 4282
6.4 |  | 8 | 88 | 20 |  | 149 |  |  |  | 265 | [20 empty] | 42511
6.5 |  | 2 | 24 |  |  | 50 |  |  |  | 76 | [20 empty] | 11908
6.6 |  | 2 | 6 | [6 empty] | 8 | [13 empty] | 15180 | 500 |  |  |  |  | 15680 | 17382
6.7 |  | 2 | 10 |  |  | 40 |  |  |  | 52 | [20 empty] | 7870
6.8 |  | 2 | 6 |  |  | 16 |  |  |  | 24 | [5 empty] | 3180 | 100 | [12 empty] | 3280 | 7142
6.9 |  | 1 | 6 | [6 empty] | 7 | [15 empty] | 9780 | 291 |  |  | 10071 | 11498
Subtotal Task 6 |  | 35 | 188 | 32 |  | 255 |  |  |  | 510 |  | 4760 |  |  |  | 5465 | 200 |  |  |  |  | 26328 | 2149 | 15180 | 500 | 9780 | 291 |  |  | 64653 | 150079
STAGE 3 | [11 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 619992
Task 7 -
7.1
7.2
7.3
TOTAL FOR STAGES 1, 2 and 3
0
[8 empty] | TOTAL BASE FEE BY FIRM |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 619992
[8 empty] | BASE FEE PLUS TASK 7 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 670000
|  |  |  | PERCENT OF TOTAL BASE CONTRACT AMOUNT BY FIRM | [7 empty] | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  |  | 0%
PERCENT OF TOTAL NOT TO EXCEED CONTRACT AMOUNT BY FIRM (Including Task 7) | [11 empty] | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  |  | 0%
Highlighted text indicates SLEB

## Sample
COMPANY NAME | [29 empty] | 2012-05-09
Proposal for Alameda County Public Works Agency
Civil Engineering, Environmental, and Right-of-Way Services for the Strobridge Avenue Extension Project
TASK | Mark Thomas & Company Labor Hours J. Sims L. Lau Project Civil Structural Project Sr Design Survey Project Survey Manager Leader Engr Engr Engr Manager Surveyor Crew | Company (Name) Labor Hours | [7 empty] | (Prime) LABOR TOTAL | Prime COST SUBTOTAL | Traffic TJKM (SLEB) |  | Environmental ICF |  | Hydrology Wreco (SLEB) |  | Hazardous Geocon |  | Geotech CE&G (SLEB) |  | VA Study VMS |  | Right of Way OPC |  | Landscape PGA (SLEB) |  | Mapping GeoCADD (SLEB) |  | SUBTOTAL Subs | TOTAL ESTIMATED COSTS
|  | (Name) Project Manager | (Name) Project Engr | (Name), Title | (Name), Title | (Name), Title | (Name), Title | (Name), Title | (Name), Title |  |  | Fee | Reimb | Fee | Reimb | Fee | Reimb | Fee | Reimb | Fee | Reimb | Fee | Reimb | Fee | Reimb | Fee | Reimb | Fee | Reimb
|  | 175 | 125 | XX.XX$/hr. | XX.XX$/hr. | XX.XX$/hr. | XX.XX$/hr. | XX.XX$/hr. | XX.XX$/hr.
STAGE 1 | [11 empty] | 40550 | 3820 | 6138 |  | 7610 | 200 | 3300 | 200 | 44280 | 1668 | 13460 | 592 |  |  |  |  | 35919 | 5950 | 163687 | 207923
Task 1 - Project Management
1.1 Project Administration and Supervision
a. Supervise, Coordinate, and Monitor Team |  | 8 | 32 | [6 empty] | 40 | [20 empty] | 0
b. Attend Kickoff Meeting |  | 2 | 2 | [6 empty] | 4 | [20 empty] | 0
c. Data Collection/Document Reviews |  |  | 4 | [6 empty] | 4 | [20 empty] | 0
d. Monthly Invoices and Progress Reports |  | 2 | 16 | [6 empty] | 18 | [20 empty] | 0
e. Quality Assurance / Quality Control |  | 16 | [7 empty] | 16 | [20 empty] | 0
f. Maintain Project Schedule |  | 4 | 16 | [6 empty] | 20 | [20 empty] | 0
1.2 Project Meetings
a. PDT Meetings (4) |  | 8 | 8 | [6 empty] | 16 | [20 empty] | 0
b. Public Workshop Meetings (2) |  | 8 | 24 |  |  | 40 |  |  |  | 72 | [20 empty] | 0
c. Design Coordination Meetings (6) |  | 2 | 18 | [6 empty] | 20 | [20 empty] | 0
d. Client Meetings (5) |  | 10 | 10 | [6 empty] | 20 | [20 empty] | 0
e. Agency Meetings (2) |  | 4 | 4 | [6 empty] | 8 | [20 empty] | 0
Subtotal Task 1 |  | 52 | 80 |  |  | 40 | 0 | 0 | 0 | 172 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
Task 2 - Prepare Technical Information
2.1 Traffic Forecasting
2.1.1 Project Corridor Evaluation |  | 2 | 2 | [6 empty] | 4 |  | 27650 | 3820 | [16 empty] | 31470 | 31470
2.1.2 Traffic Operations Analysis |  | 1 | 2 | [6 empty] | 3 |  | 8880 | [17 empty] | 8880 | 8880
2.2 Base Mapping Development
2.2.1 Prepare Aerial Mapping |  | 1 | 7 |  |  |  | 14 | 58 | 68 | 148 | [17 empty] | 35919 | 5950 | 41869 | 41869
2.2.2 Supplemental Topographic Survey |  | 1 | 3 |  |  |  | 4 | 24 | 40 | 72 | [20 empty] | 0
2.2.3 Research and Data Collection |  |  | 3 |  |  | 16 | 4 | 16 |  | 39 | [20 empty] | 0
2.2.4 Utility Investigation |  |  | 3 |  |  | 16 |  |  |  | 19 | [20 empty] | 0
2.2.5 Record Boundary | [6 empty] | 24 | 48 |  | 72 | [20 empty] | 0
2.3 Environmental Impact Analysis |  | 2 | 2 | [6 empty] | 4 | [5 empty] | 4770 | 200 | 3300 | 200 | [10 empty] | 8470 | 8470
2.4 Geotechnical Investigations |  | 2 | 4 | [6 empty] | 6 | [9 empty] | 44280 | 1668 | [8 empty] | 45948 | 45948
Subtotal Task 2 |  | 9 | 26 |  |  | 32 | 46 | 146 | 108 | 367 |  | 36530 | 3820 |  |  | 4770 | 200 | 3300 | 200 | 44280 | 1668 | [6 empty] | 35919 | 5950 | 136637 | 136637
Task 3 - Develop Alternatives
3.1 Develop Conceptual Alternatives |  | 16 | 120 | 40 |  | 216 |  |  |  | 392 |  | 4020 |  | 6138 |  | 2840 | [13 empty] | 12998 | 12998
Subtotal Task 3 |  | 16 | 120 | 40 |  | 216 |  |  |  | 392 |  | 4020 |  | 6138 |  | 2840 | [13 empty] | 12998 | 12998
Task 4 - Prepare Alternative Analysis
4.1 Develop Evaluation Criteria, Project Reference Sheets & Tech Memo |  | 8 | 68 | [6 empty] | 76 | [20 empty] | 15256
4.2 Identify and Screen Alternatives |  | 4 | 80 | 16 | [5 empty] | 100 | [20 empty] | 19100
4.3 Two Day Improvements Prioritization Workshops |  | 4 | 16 | [6 empty] | 20 | [11 empty] | 13460 | 592 | [6 empty] | 14052 | 18224
4.4 Determine Viability of Alternatives |  | 4 | 24 | [6 empty] | 28 | [20 empty] | 5708
Subtotal Task 4 |  | 20 | 188 | 16 | [5 empty] | 224 | [11 empty] | 13460 | 592 | [6 empty] | 14052 | 58288
STAGE 2 | [11 empty] | 4760 |  | 32897 | 5445 | 15610 | 400 |  |  |  |  | 26328 | 2149 | 15180 | 500 | 9780 | 291 |  |  | 113340 | 204038
Task 5 -
5.1 | [13 empty] | 2000 | [15 empty] | 2000 | 2000
5.2 |  | 4 | 8 | [6 empty] | 12 |  |  |  | 20698 |  | 6510 | 100 | [12 empty] | 27308 | 29944
5.3 |  | 4 | 8 | [6 empty] | 12 |  |  |  | 10199 | 5445 | 3635 | 100 | [12 empty] | 19379 | 22015
Subtotal Task 5 |  | 8 | 16 | [6 empty] | 24 |  |  |  | 32897 | 5445 | 10145 | 200 | [12 empty] | 48687 | 53959
Task 6 -
6.1 |  | 8 | 24 | [6 empty] | 32 |  | 4760 | [17 empty] | 4760 | 11568
6.2 |  | 8 | 8 | 8 | [5 empty] | 24 | [5 empty] | 2285 | 100 |  |  |  |  | 26328 | 2149 | [6 empty] | 30862 | 35918
6.3 |  | 2 | 16 | 4 | [5 empty] | 22 | [20 empty] | 4282
6.4 |  | 8 | 88 | 20 |  | 149 |  |  |  | 265 | [20 empty] | 42511
6.5 |  | 2 | 24 |  |  | 50 |  |  |  | 76 | [20 empty] | 11908
6.6 |  | 2 | 6 | [6 empty] | 8 | [13 empty] | 15180 | 500 |  |  |  |  | 15680 | 17382
6.7 |  | 2 | 10 |  |  | 40 |  |  |  | 52 | [20 empty] | 7870
6.8 |  | 2 | 6 |  |  | 16 |  |  |  | 24 | [5 empty] | 3180 | 100 | [12 empty] | 3280 | 7142
6.9 |  | 1 | 6 | [6 empty] | 7 | [15 empty] | 9780 | 291 |  |  | 10071 | 11498
Subtotal Task 6 |  | 35 | 188 | 32 |  | 255 |  |  |  | 510 |  | 4760 |  |  |  | 5465 | 200 |  |  |  |  | 26328 | 2149 | 15180 | 500 | 9780 | 291 |  |  | 64653 | 150079
STAGE 3 | [11 empty] | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 619992
Task 7 -
7.1
7.2
7.3
TOTAL FOR STAGES 1, 2 and 3
0
[8 empty] | TOTAL BASE FEE BY FIRM |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 619992
[8 empty] | BASE FEE PLUS TASK 7 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 670000
|  |  |  | PERCENT OF TOTAL BASE CONTRACT AMOUNT BY FIRM | [7 empty] | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  |  | 0%
PERCENT OF TOTAL NOT TO EXCEED CONTRACT AMOUNT BY FIRM (Including Task 7) | [11 empty] | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  |  | 0%
Highlighted text indicates SLEB
Sample

## Table 1
COMPANY NAME | [29 empty] | 2012-05-09
Proposal for Alameda County Public Works Agency
Civil Engineering, Environmental, and Right-of-Way Services for the Strobridge Avenue Extension Project
TASK | Mark Thomas & Company Labor Hours J. Sims L. Lau Project Civil Structural Project Sr Design Survey Project Survey Manager Leader Engr Engr Engr Manager Surveyor Crew | Company (Name) Labor Hours | [7 empty] | (Prime) LABOR TOTAL | Prime MTCo COST SUBTOTAL | Traffic TJKM (SLEB) |  | Environmental ICF |  | Hydrology Wreco (SLEB) |  | Hazardous Geocon |  | Geotech CE&G (SLEB) |  | VA Study VMS |  | Right of Way OPC |  | Landscape PGA (SLEB) |  | Mapping GeoCADD (SLEB) |  | SUBTOTAL Subs | TOTAL ESTIMATED COSTS
|  | (Name) Project Manager | (Name) Project Engr | (Name), Title | (Name), Title | (Name), Title | (Name), Title | (Name), Title | (Name), Title |  |  | Fee | Reimb | Fee | Reimb | Fee | Reimb | Fee | Reimb | Fee | Reimb | Fee | Reimb | Fee | Reimb | Fee | Reimb | Fee | Reimb
|  | 175 | 125 | XX.XX$/hr. | XX.XX$/hr. | XX.XX$/hr. | XX.XX$/hr. | XX.XX$/hr. | XX.XX$/hr.
Task 1 - Perform Project Management
1.1 Project Administration and Supervision
a. Supervise, Coordinate, and Monitor Team |  | 8 | 32 | [6 empty] | 40 | #VALUE! | [19 empty] | #VALUE!
b. Attend Kickoff Meeting |  | 2 | 2 | [6 empty] | 4 | #VALUE! | [19 empty] | #VALUE!
c. Data Collection/Document Reviews |  |  | 4 | [6 empty] | 4 | #VALUE! | [19 empty] | #VALUE!
d. Monthly Invoices and Progress Reports |  | 2 | 16 | [6 empty] | 18 | #VALUE! | [19 empty] | #VALUE!
e. Quality Assurance / Quality Control |  | 16 | [7 empty] | 16 | #VALUE! | [19 empty] | #VALUE!
f. Maintain Project Schedule |  | 4 | 16 | [6 empty] | 20 | #VALUE! | [19 empty] | #VALUE!
g. Encroachment Permits |  | 2 | 8 | [6 empty] | 10 | #VALUE! | [19 empty] | #VALUE!
1.2 Project Meetings
a. PDT Meetings (4) |  | 8 | 8 | [6 empty] | 16 | #VALUE! | [19 empty] | #VALUE!
b. Public Workshop Meetings (2) |  | 8 | 24 |  |  | 40 |  |  |  | 72 | #VALUE! | [19 empty] | #VALUE!
c. Design Coordination Meetings (6) |  | 2 | 18 | [6 empty] | 20 | #VALUE! | [19 empty] | #VALUE!
d. Client Meetings (5) |  | 10 | 10 | [6 empty] | 20 | #VALUE! | [19 empty] | #VALUE!
e. Agency Meetings (2) |  | 4 | 4 | [6 empty] | 8 | #VALUE! | [19 empty] | #VALUE!
Subtotal Task 1 |  | 66 | 142 |  |  | 40 |  |  |  | 248 | #VALUE! | [19 empty] | #VALUE!
PHASE 1 (PART A) | [11 empty] | 40550 | 3820 | 6138 |  | 7610 | 200 | 3300 | 200 | 44280 | 1668 | 13460 | 592 |  |  |  |  | 35919 | 5950 | 163687 | #VALUE!
Task 2 - Prepare Technical Information
2.1 Traffic Forecasting
2.1.1 Project Corridor Evaluation |  | 2 | 2 | [6 empty] | 4 | #VALUE! | 27650 | 3820 | [16 empty] | 31470 | #VALUE!
2.1.2 Traffic Operations Analysis |  | 1 | 2 | [6 empty] | 3 | #VALUE! | 8880 | [17 empty] | 8880 | #VALUE!
2.2 Base Mapping Development
2.2.1 Prepare Aerial Mapping |  | 1 | 7 |  |  |  | 14 | 58 | 68 | 148 | #VALUE! | [16 empty] | 35919 | 5950 | 41869 | #VALUE!
2.2.2 Supplemental Topographic Survey |  | 1 | 3 |  |  |  | 4 | 24 | 40 | 72 | #VALUE! | [19 empty] | #VALUE!
2.2.3 Research and Data Collection |  |  | 3 |  |  | 16 | 4 | 16 |  | 39 | #VALUE! | [19 empty] | #VALUE!
2.2.4 Utility Investigation |  |  | 3 |  |  | 16 |  |  |  | 19 | #VALUE! | [19 empty] | #VALUE!
2.2.5 Record Boundary | [6 empty] | 24 | 48 |  | 72 | #VALUE! | [19 empty] | #VALUE!
2.3 Environmental Impact Analysis |  | 2 | 2 | [6 empty] | 4 | #VALUE! |  |  |  |  | 4770 | 200 | 3300 | 200 | [10 empty] | 8470 | #VALUE!
2.4 Geotechnical Investigations |  | 2 | 4 | [6 empty] | 6 | #VALUE! | [8 empty] | 44280 | 1668 | [8 empty] | 45948 | #VALUE!
Subtotal Task 2 |  | 9 | 26 |  |  | 32 | 46 | 146 | 108 | 367 | #VALUE! | 36530 | 3820 |  |  | 4770 | 200 | 3300 | 200 | 44280 | 1668 | [6 empty] | 35919 | 5950 | 136637 | #VALUE!
Task 3 - Develop Alternatives
3.1 Develop Conceptual Alternatives |  | 16 | 120 | 40 |  | 216 |  |  |  | 392 | #VALUE! | 4020 |  | 6138 |  | 2840 | [13 empty] | 12998 | #VALUE!
Subtotal Task 3 |  | 16 | 120 | 40 |  | 216 |  |  |  | 392 | #VALUE! | 4020 |  | 6138 |  | 2840 | [13 empty] | 12998 | #VALUE!
Task 4 - Prepare Alternative Analysis
4.1 Develop Evaluation Criteria, Project Reference Sheets & Tech Memo |  | 8 | 68 | [6 empty] | 76 | 15256 | [19 empty] | 15256
4.2 Identify and Screen Alternatives |  | 4 | 80 | 16 | [5 empty] | 100 | 19100 | [19 empty] | 19100
4.3 Two Day Improvements Prioritization Workshops |  | 4 | 16 | [6 empty] | 20 | 4172 | [10 empty] | 13460 | 592 | [6 empty] | 14052 | 18224
4.4 Determine Viability of Alternatives |  | 4 | 24 | [6 empty] | 28 | 5708 | [19 empty] | 5708
Subtotal Task 4 |  | 20 | 188 | 16 | [5 empty] | 224 | 44236 | [10 empty] | 13460 | 592 | [6 empty] | 14052 | 58288
PHASE 2 (PART B) | [11 empty] | 4760 |  | 32897 | 5445 | 15610 | 400 |  |  |  |  | 26328 | 2149 | 15180 | 500 | 9780 | 291 |  |  | 113340 | 229118
Task 5 - Preliminary Environmental Analysis Report (PEAR)
5.1 Project Site Review/Windshield Survey | [13 empty] | 2000 | [15 empty] | 2000 | 2000
5.2 Prepare Draft PEAR |  | 4 | 8 | [6 empty] | 12 | #VALUE! |  |  | 20698 |  | 6510 | 100 | [12 empty] | 27308 | 29944
5.3 Prepare Final PEAR |  | 4 | 8 | [6 empty] | 12 | #VALUE! |  |  | 10199 | 5445 | 3635 | 100 | [12 empty] | 19379 | 22015
Subtotal Task 5 |  | 8 | 16 | [6 empty] | 24 | #VALUE! |  |  | 32897 | 5445 | 10145 | 200 | [12 empty] | 48687 | 53959
Task 6 - Prepare Project Study Report
6.1 Identification of Alternatives |  | 8 | 24 | [6 empty] | 32 | #VALUE! | 4760 | [17 empty] | 4760 | 11568
6.2 Value Analysis Study Report |  | 8 | 8 | 8 | [5 empty] | 24 | #VALUE! |  |  |  |  | 2285 | 100 |  |  |  |  | 26328 | 2149 | [6 empty] | 30862 | 35918
6.3 Phasing for Preferred Alternatives |  | 2 | 16 | 4 | [5 empty] | 22 | #VALUE! | [19 empty] | 4282
6.4 Prepare Preliminary Geometric Plans |  | 8 | 88 | 20 |  | 149 |  |  |  | 265 | #VALUE! | [19 empty] | 42511
6.5 Mandatory and Advisory Design Exceptions |  | 2 | 24 |  |  | 50 |  |  |  | 76 | #VALUE! | [19 empty] | 11908
6.6 Prepare Preliminary Right of Way Data Sheets |  | 2 | 6 | [6 empty] | 8 | #VALUE! | [12 empty] | 15180 | 500 |  |  |  |  | 15680 | 17382
6.7 Prepare Preliminary Construction Estimates |  | 2 | 10 |  |  | 40 |  |  |  | 52 | #VALUE! | [19 empty] | 7870
6.8 Prepare Stormwater Data Report |  | 2 | 6 |  |  | 16 |  |  |  | 24 | #VALUE! |  |  |  |  | 3180 | 100 | [12 empty] | 3280 | 7142
6.9 Prepare Landscape Concept Plans |  | 1 | 6 | [6 empty] | 7 | #VALUE! | [14 empty] | 9780 | 291 |  |  | 10071 | 11498
6.10 Prepare Draft and Final Project Study Report |  | 24 | 40 |  |  | 80 |  |  |  | 144 | #VALUE! | [19 empty] | 25080
Subtotal Task 6 |  | 59 | 228 | 32 |  | 335 |  |  |  | 654 | #VALUE! | 4760 |  |  |  | 5465 | 200 |  |  |  |  | 26328 | 2149 | 15180 | 500 | 9780 | 291 |  |  | 64653 | 175159
TOTAL FOR PHASES 1 AND 2 |  | 178 | 720 | 88 |  | 623 | 46 | 146 | 108 | 1909 | #VALUE! | 45310 | 3820 | 39035 | 5445 | 23220 | 600 | 3300 | 200 | 44280 | 1668 | 39788 | 2741 | 15180 | 500 | 9780 | 291 | 35919 | 5950 | 277027 | #VALUE!
Task 7 - Project Contingency - Optional | [10 empty] | 50008 | [19 empty] | 50008
[8 empty] | TOTAL BASE FEE BY FIRM |  |  | #VALUE! | 49130 |  | 44480 |  | 23820 |  | 3500 |  | 45948 |  | 42529 |  | 15680 |  | 10071 |  | 41869 |  |  | 619992
[8 empty] | BASE FEE PLUS TASK 7 |  |  | #VALUE! | 49130 |  | 44480 |  | 23820 |  | 3500 |  | 45948 |  | 42529 |  | 15680 |  | 10071 |  | 41869 |  |  | 670000
|  |  |  | PERCENT OF TOTAL BASE CONTRACT AMOUNT BY FIRM | [6 empty] | #VALUE! | 7.924% |  | 7.174% |  | 3.842% |  | 0.5645% |  | 7.411% |  | 6.86% |  | 2.529% |  | 1.624% |  | 6.753% |  |  | 27.55%
PERCENT OF TOTAL NOT TO EXCEED CONTRACT AMOUNT BY FIRM (Including Task 7) | [10 empty] | #VALUE! | 7.333% |  | 6.639% |  | 3.555% |  | 0.5224% |  | 6.858% |  | 6.348% |  | 2.34% |  | 1.503% |  | 6.249% |  |  | 25.5%
Highlighted text indicates SLEB